## Notes
Arrange van for people transport
12:30-13:30 lunch
Separate color bands (for 3 types of food()
Big signs print of area: breakout1, breakout2, main stage, small stage, lunch.
Canpoy in back of mind>
Little stage for speakers higher rent (2x4 neter)
TV or maybe just print big schedule for next to main stage
Make map with areas for ourselve
Banner next to stage from MPB
Recording on Kids section
after lunch, prep breakout areas in two circles

## Expenses
Income |  |  |  | Expenses | Paid | Unpaid
5550 |  |  |  | 5624 | 2178 | 3446
Status | Item | Unit Price | Quantity | Extended |  |  | Notes
Venue
Decided | Total price | 4356 | 1 | 4356 | 2178 | 2178 | 50% paid
Closed | Director Security | 0 | 1 | 0 |  | 0
Closed | Insurance | 0 | 1 | 0 | 0 | 0
|  |  |  | 4356 | 2178 | 2178
Food
Closed | Snacks | 0 | 1 | 0 | 0 | 0
Closed | Coffee & Tea | 0 | 1 | 0 | 0 | 0
Closed | Alcohol | 0 | 1 | 0 | 0 | 0 | included, write on wristband if already received.
Open | Speakers dinner after | 200 | 1 | 200 | 0 | 200 | 15 team, 5 speaker, 10usd each - pupusa
Closed | Food trucks | 0 | 1 | 0 | 0 | 0
|  |  |  | 200 | 0 | 200
Equipment
Closed | Tent + tables + chairs | 0 | 1 | 0 | 0 | 0 | enough placed available indoor if it starts to rain
Decided | 4x microphones, audio | 300 | 1 | 300 | 0 | 300
Open | Recordings video | 300 | 1 | 300 | 0 | 300
Open | Whiteboard + markers | 0 | 1 | 0 | 0 | 0
|  |  |  | 600 | 0 | 600
General Administration
Closed | Travel, lodging, etc | 0 | 1 | 0 | 0 | 0
Open | Marketing | 50 | 1 | 50 | 0 | 50 | edit video with rafael
Open | Flyers | 20 | 1 | 20 | 0 | 20
Open | Schedule printed sheet | 40 | 1 | 40 | 0 | 40 | print 5 schedules once initial speeakers are confirmed
Open | Stamp for marking beer/food | 10 | 1 | 10 | 0 | 10
Open | T-shirts | 161 | 1 | 161 | 0 | 161 | 7 usd per shirt, 20 team, 3 volunteers
Open | Wristbands | 150 | 1 | 150 | 0 | 150 | either fanncy, either cheap, or the one for free from Cadejo
Open | Fundraising props, e.g., stickers | 20 | 1 | 37 | 0 | 37
|  |  |  | 468 | 0 | 468

## Income
| Max capacity |  |  |  | 150 |  | Invited Guests
[7 empty] | 1 | name
| Ticket type | Attendees | Paying % | Ticket Price | Revenue |  | 2 | name
| Early Bird | 50 | 30% | 35 | 1750 |  | 3
| Veteran / Student | 0 | 21% | 0 | 0 |  | 4
| Regular | 70 | 39% | 40 | 2800 |  | 5
| Last Minute | 20 | 10% | 50 | 1000 |  | 6
| Volunteers / Staff | 20 |  |  | 0 |  | 7
| Invited Guests | 10 |  |  | 0 |  | 8
| Total | 170 | 100% |  | 5550 |  | 9
10
| Paying | 140
| Non-Paying | 30
15% | Expected with No-Shows | 145
| SOLD SO FAR | Total | week of | week of | week of | week of | week of | week of | week of | week of | week of | week of | week of
|  |  | 2024-09-06 | 2024-09-13 | 2024-09-20 | 2024-09-27 | 2024-10-04 | 2024-10-11 | 2024-10-18 | 2024-10-25 | 2024-11-01 | 2024-11-08 | 2024-11-15
| Early Bird | 50 | 2024-09-06: 10
| Veteran / Student | 0 | 2024-09-06: 0
| Regular Price | 70 | 2024-09-06: 0
| Last Minute | 20 | 2024-09-06: 0
| Volunteers / Staff | 20 | 2024-09-06: 20
| Invited Guests | 10 | 2024-09-06: 0
| Total | 170 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Paying | 140 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Non-Paying | 30 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 7.143% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | 10% | 20% | 30% | 40% | 50% | 60% | 70% | 80% | 90% | 110%
| Speaker applications |  | 10%: 2

## VolunteersTeamSpeakers
Start | end | item | Volunteer | item | Amount
10:00 | 11:00 | open doors | Teachers | Setup (chairs, tablecloth) | 5
11:00 | 12:00 | day-of intro/pitch | Gerardo | Check-in / front desk (wristbands) | 2
12:00 | 13:00 | lunch | Quentin
13:00 | 14:00 | start session 1 at 1pm | extern | Audio responsible | 2
14:00 | 15:00 | start session 2 at 2pm | extern |  | 3
15:00 | 16:00 | start session 3 at 3pm | Roberto | MC | 3
16:00 | 17:00 | start session 4 at 4pm | to be done | MC
17:00 | 18:00 | start session 5 at 5pm | to be done | Assist the MC (rounding up people between workshops)
18:00 | 19:00 | closing words, cleaning 18:15 | Wally | Photos, videos, testimonials | 1
19:00 |  | leave the latest | ----- | Fundraising on-ground | 0
|  |  | Marvin | Tear down | 5
Volunteer |  | Shirt size | Daniel
John |  |  | Jorge Luis
Adam |  |  | Jesus
Quentin |  |  | Gerardo
Emilio |  |  | Arnold | Day-of discussions collection, communication | 1
Arnold |  |  | Arnold | Schedule updates, planning, timing | 1
Reyna
Roberto
Jonathan |  |  | Action item list
Marvin |  |  | ask kitchen how much time they need |  | Emilio
Daniel |  |  | Pop up on website |  | Arnold
Jorge Luis |  |  | Press release |  | Arnold
Jesus |  |  | Photos layout website bigger phone |  | Arnold
Gerardo |  |  | Think of MC’s |  | Both
Hector |  |  | Flyer |  | Emilio
Miguel
Dax
Wally |  |  | MC's Arnold: Afrat, Jamie, Niky/James,
Scott | ?
volunteer1
volunteer2
voluteer3
Speakers
1 |  | Dusan Matuska
2 |  | Roger Huang
3 |  | Maya Parbhoe | Invite speakers/educators Adopting |  | Who to reach out
4 |  | Hermann Buhr-Vivier | Hermann Buhr-Vivier |  | Arnold
5 |  | Felix Mukungu | Giacomo Zucco
6 |  | Fidel Funez | Benjamin de Waal |  | Arnold
7 |  | Gabe Lord | Mike Peterson
8 |  | MPB Teachers | Nicolas Burtey
9 |  |  | Roman Martínez
10 |  |  | Efrat Fenigson
11 |  |  | Dusan Matuska |  | Arnold
12 |  |  | Fidel Funez |  | Arnold
13 |  |  | Luke Mikic |  | Arnold
14 |  |  | Richard Taylor
15 |  |  | Aleksandar Svetski |  | Arnold
16 |  |  | André Loja
17 |  |  | Deanna Heikkinen
18 |  |  | Nicki & James
19 |  |  | Roger Huang |  | Arnold
20 |  |  | Maya Parbhoe |  | Arnold
|  |  | Adam Cowperthwait |  | Arnold
|  |  | Gabe Lord |  | Arnold