## Planning
| change the date below |  |  | MONTH -3 |  |  |  | MONTH -2 |  |  |  | MONTH -1
EVENT DATE | 2024-11-14 | ASAP | pre WEEK -12 | WEEK -12 | WEEK -11 | WEEK -10 | WEEK -9 | WEEK -8 | WEEK -7 | WEEK -6 | WEEK -5 | WEEK -4 | WEEK -3 | WEEK -2 | WEEK -1 | EVENT | WEEK +1 | WEEK +2 | WEEK +3 | WEEK +4
|  |  | 2024-08-15 | 2024-08-22 | 2024-08-29 | 2024-09-05 | 2024-09-12 | 2024-09-19 | 2024-09-26 | 2024-10-03 | 2024-10-10 | 2024-10-17 | 2024-10-24 | 2024-10-31 | 2024-11-07 | 2024-11-14 | -28 | -21 | -14 | -7
0. ORGANIZATIONAL FLOW
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1. PREPARE FIRST STEPS
Decide: connect to a bigger conference nearby (optional) |  | FALSE
Decide: find/delegate people to the task (job & roles) |  | FALSE
Decide: affiliated to MPB or independent event |  | FALSE
Notice: Mi Primer Bitcoin (MPB) doesn’t take sponsorships |  | FALSE
Decide: team up with Light/Full Nodes |  | FALSE
Decide: mission versus finance |  | FALSE
Branding Policy |  | FALSE
Write onepager |  | FALSE
2. ROLE CLARITY
Local leader |  |  | FALSE
Local support group |  |  | FALSE
Create Telegram/Signal group for volunteers | [6 empty] | FALSE
3. FINANCE
Budgetting |  |  |  |  | FALSE | FALSE
Quotes
Ticket price | [5 empty] | FALSE
Sponsorship
4. VENUE
Research options |  | FALSE | FALSE
Lock in venue |  |  |  | FALSE
Event liability Insurance | [7 empty] | FALSE
Lock in equip partner | [10 empty] | FALSE
Lock in labor services | [7 empty] | FALSE
Lock in food truck | [9 empty] | FALSE
5. TECH
Website |  |  |  |  | FALSE
Ticket sale |  |  |  |  | FALSE
Popup website | [5 empty] | FALSE
6. MARKETING + BRANDING
Save the Date |  | FALSE | FALSE
Event date communication |  | FALSE
Theme |  |  | FALSE
Collaborations |  |  | FALSE
Press Release | [5 empty] | FALSE
Post about location | [8 empty] | FALSE | FALSE
Copy for website |  |  |  |  | FALSE | FALSE
Trailer | [6 empty] | FALSE
Testimonies | [10 empty] | FALSE |  |  |  |  | FALSE
Flyer |  |  |  |  | FALSE |  |  | FALSE |  |  | FALSE
Throwback to previous Unconferences | [9 empty] | FALSE
Reminder available Early Bird Tickets | [7 empty] | FALSE
Speaker announcements | [11 empty] | FALSE | FALSE | FALSE
Speaker Form send to current attendees list | [9 empty] | FALSE
Speaker Form on socials | [9 empty] | FALSE | FALSE | FALSE
Schedule preparation | [11 empty] | FALSE | FALSE
Schedule announcement | [12 empty] | FALSE | FALSE
7. OPERATIONS
Find high name speakers |  |  |  |  | FALSE
Speaker/workshops form on website | [5 empty] | FALSE
Speaker/workshops decide/review | [12 empty] | FALSE
Contact with volunteers | [6 empty] | FALSE
List of duty for volunteers | [12 empty] | FALSE
Give tickets to volunteers | [8 empty] | FALSE
Initial meeting workshops | [8 empty] | FALSE
Operations during the day | [8 empty] | FALSE
Print Schedule on-site | [10 empty] | FALSE
Sent Tickets to speakers | [10 empty] | FALSE
Send email to all attendees with schedule | [10 empty] | FALSE
Prepare slider background | [10 empty] | FALSE
Print schedule | [14 empty] | FALSE
8. MPB Props Kit
Merchandise | [5 empty] | prepare: | FALSE | execute: | FALSE
Wristband | [7 empty] | FALSE
MPB Flyers | [9 empty] | FALSE
Banners | [12 empty] | FALSE
Shirt for flyer | [9 empty] | FALSE
Scanner/phone | [13 empty] | FALSE
Laptop | [13 empty] | FALSE
Microphones | [8 empty] | FALSE
Whiteboard
Projector | [7 empty] | FALSE
9. Aftercare
Gratitude to speakers | [16 empty] | FALSE
Feedback form to attendees | [16 empty] | FALSE
Collect recordings, photo materials | [16 empty] | FALSE
Formulas:
pre WEEK -12 = [MONTH -3]-7
EVENT = [change the date below, row above]
WEEK +1 = [WEEK +2]-7

## Roles
Executive sponsor | name a
Event Lead | name b
Tech Lead | name c
Marketing/Communications | name d
Creatives | name e